## Table of hours
NOTE: All those times are aproximations and the mejority are yet in progress so we've to add more hours
| Roger Tello | Oliver Cabezas | Andrey Ivanov | Rodrigo de Pedro
Exctract all sprites in sprite_list from MAME. | 10 hours | 12 hours | 11 hours
Find and take note of every visual element of the level. This includes: scenario elements (including destroying sprites), enemies (all sprites including deaths), NPCs(being hit sprites too), power ups, particles (enemies shots), UI and backgrounds. Create a list called sprite_list. |  | 7 hours | 6 hours
Group all sprites in pngs (particles spritesheet, enemies spritesheet...) working with the code section. |  | 2 hours | 2 hours
Resize sprites if needed and possible art problem fixes. | 2 hours |  | 3 hours
Find all FX and music needed and label it. | 1 hour 30 min | 3 hours
Organize all sound files and convert to .ogg if necessary. | 15 min | 15 min
Check that every sound is like the original game and possible sound problem fixes. | 5 min
Check every piece of new code as it's been implemented to find bugs early. |  |  | 3 hours
Check if animations, enemy spawn times, difficulty, etc. is like the original game. |  |  | 2 hours
Bug tracking and recording for the alpha.
Debug current version so it has no bugs and we can start coding with a "clean" base. | 2 hours
Code debug functionalities: god mode, win & loose condition… | 1 hour 30 min
Clean, optimize, make readable and organize all code. | 1 hour 30 min |  | 2 hours
Implement features not done yet, including: dynamite throw, working UI, state machines, etc. | 1 hours
TOTAL HOURS

## Tasks to do
Exctract all sprites in sprite_list from MAME. | take the sprites of all the enemies again with another color for when they're being hited (just aply a layer in photoshop) (20 min)
Find and take note of every visual element of the level. This includes: scenario elements (including destroying sprites), enemies (all sprites including deaths), NPCs(being hit sprites too), power ups, particles (enemies shots), UI and backgrounds. Create a list called sprite_list.
Group all sprites in pngs (particles spritesheet, enemies spritesheet...) working with the code section. | Have the spritesheet of all the sprites necessary for the enemies (such as enemie jumping, zepelin shots..) (1 day)
Resize sprites if needed and possible art problem fixes.
Find all FX and music needed and label it.
Organize all sound files and convert to .ogg if necessary.
Check that every sound is like the original game and possible sound problem fixes. | find sound of the wall breaking (30 min)
Check every piece of new code as it's been implemented to find bugs early.
Check if animations, enemy spawn times, difficulty, etc. is like the original game. | when the main character is moving right, he has a different speed velocity than when is moving left. (10 min) | chek the general polish of the game (till the gold)
Bug tracking and recording for the alpha.
Debug current version so it has no bugs and we can start coding with a "clean" base.
Code debug functionalities. | Check with mame and assign the correct order for the screens, feeting the same music.(1 hour) | implement the animation when the player wins (1 day)
Clean, optimize, make readable and organize all code. | change the names of everything it's not from the game, say ModuleSceneSpace (1 day)
Implement features not done yet, including: dynamite throw, working UI, state machines, etc. | implements fonts of the initial screen to the game (polish) (1 day) | implement the dynamite throw (2 days) | implement live for the player, it need to be killed 3 times, ideally to have a respawn (3 days) | polish animations of the chracters (till the gold) | implement the zeppelin (3 days) | make the enemy able to jump to the floor level (2 days) | implement the other 2 weapons. (3 days) | implement the counter for the progress of the level(3 days) | implement scoore(3 days) | make the enemies change color for one frame when is being hited (1 day)